## Slide 1: Implementing Evidence-based Interventions
Module created in partnership with
Population Improvement Partners
www.improvepartners.org
The Cancer Prevention and Control Research Network is supported by Cooperative Agreement Number 3 U48 DP005017-01S8 from the Centers for Disease Control and Prevention’s Prevention Research Centers Program and the National Cancer Institute. The content of this curriculum is based upon findings and experiences of workgroup members and does not necessarily represent the official position of the funders.
Notes: Talking Points:
We covered Planning for Evaluation early in this training before the Finding, Selecting, and Adapting sessions. This helps you keep evaluation in mind throughout the planning process.
Now we will delve deeper into implementation as they apply to existing evidence-based strategies.

## Slide 2: Where Do We Stand?
*Adapted from Brownson et al. (2011). Evidence-Based Public Health. 2nd ed. New York, NY: Oxford University Press.
Assessing your Community
Implementing & Evaluating
Establishing Goals & Objectives
Finding EBI
Selecting Best Fitting EBI
Adapting EBI
Notes: Talking Points:
At this point in the process, you have selected an evidence-based strategy that is compatible with your community and context.
You have also considered how to adapt it to increase fit.
Now strategic implementation plans are needed to ensure implementation fidelity and quality.

## Slide 3: Session Objectives
Describe successful intervention implementation
Discuss quality improvement (QI) tools to help your team plan for and implement selected strategies
Describe key tasks in planning, implementation, evaluation, and maintenance
Notes: Talking Points:
In this session, we will:
Describe successful program implementation
Discuss quality improvement (QI) tools to help your team plan for and implement selected strategies
Describe key tasks in planning, implementation, evaluation, and maintenance

## Slide 4
=
Positive Outcomes
Source: State Implementation and Scaling-up of Evidence–based Practices
Effective Interventions
+
Effective Implementation
CDC Community Guide
National Cancer Institute
RTIPS
What Works for Health
Others?
Notes: Talking Points:
Bridge: What creates a positive outcome when we are implementing a strategy?
Show the formula and discuss it
If you have an effective strategy but don’t implement it effectively then you can’t expect a positive outcome.
If you have an ineffective strategy and effective implementation you can’t expect positive outcomes
Key points:
You must identify effective strategies –from the Finding Evidence module, with core elements. (You have discussed how to do this in previous modules)
This module will discuss how to plan implementation efforts so they are effective.

## Slide 5: Steps to Planning for Implementation
Create an implementation team
Assess your organization's/coalition's readiness
Select “early adopters” to do a small pilot test to understand and learn how to adapt/adjust implementation efforts
Use improvement cycles to learn what works, what creates barriers, and what can be improved
Draft an implementation plan
Durlak, J.A., & DuPre, E.P. (2008) Implementation matters: A review of research on the influence of implementation of program outcomes and the factors affecting implementation. Am J Com Psych. 41:327-350.
Notes: Talking Points:
As you plan an implementation work plan, keep in mind there are certain characteristics that lead to implementation quality and higher levels of fidelity, as discussed in the previous session.
Community level engagement (funding, policy, politics) – A supportive community environment is important. This may include funding support from leaders, supportive pre-existing policies, or a political dynamic that facilitates your work.
Provider/implementer characteristics – The key individuals involved can affect implementation quality. The champions, main stakeholders, and especially the implementers need to see the:
  Need for the innovation or EBS
  Benefits of innovation/EBS
  Self-efficacy – They should think they are capable of delivering the EBS.
  Skill proficiency for implementation – They should actually possess the skills or training needed to implement the EBS.

## Slide 6: 1. Create an Implementation Team
An Implementation Team:
Makes the strategy happen
Engages stakeholders
Creates readiness for implementation
Ensures fidelity
Provides TA and support to overcome barriers
Monitors outcomes and feedback to improve implementation
Sources: National Implementation Research Network and SAMSHA
Notes: Talking Points:
To ensure that a strategy is implemented effectively, it is important that a team is established to monitor and “drive” the implementation.
An implementation team:
  Makes the strategy happen
  Engages stakeholders
  Creates readiness for strategy
  Ensures fidelity
  Provides TA and support to overcome barriers
  Monitors outcomes and feedback to improve implementation

## Slide 7: Members of an Implementation Team
Content Expertise: implement with fidelity
Program Management: implement on time and under budget
Quality Improvement: monitor data and continuously adapt implementation process
“Customer Perspective”: include view point of someone who will be using the strategy/intervention in their daily life
Partner Representation: provide resources, expertise, and staff to help implement
Notes: Talking Points:
The following is a list of “implementation characteristics” that is important for a successful team.
  Content Expertise: your team should consist of someone who is knowledgeable about the strategy and can ensure it is implemented with fidelity
  Program Management: your team should consist of someone who has program management skills to monitor the timeline and budget of the strategy
  Quality Improvement: your team should consist of someone who can monitor the data with frequency and help the team continuously adapt the implementation process to ensure it is successful
  “Customer Perspective”: although your team may not have a customer directly part of the team (however we highly recommend that if at all possible) you should think of ways to ensure the view point of someone who will be using/impacted by the strategy or intervention gives feedback and helps shape how things are implemented
  Partner Representation-your team should consists of partners that can provide resources, expertise, and staff to implement
A couple of tips for selecting the team:
Consider having at least 4-6 team members
Think about your strategy/intervention. Make sure the team members “match” the intervention or strategy. If you are implementing a healthy eating program in schools you would want to make sure you had school reps, parents, students, etc. on the team.
DON’T‘ forget to include “customers and partners. What strategies have you used to keep customers and partners engaged and at the table?

## Slide 8: Trivia Question
What percent of evidence-based strategies are effective without an Implementation Team?
Notes: Talking Points:
Allow participants to read the questions and answer it.
Answer is: Less than 14% are effective and it takes 7 years to implement
vs.
An evidence-based strategy that has an Implementation Team that uses proven methods in Implementation Science—they are 80% effective and it takes 3 years to implement.
Source: NIRN http://nirn.fpg.unc.edu/learn-implementation/implementation-stages

## Slide 9: Program Charter
Content Created by Population Health Improvement Partners
Aims and objectives
Deliverables
Scope
Team members and roles
Team meeting schedule
Senior leadership support
Notes: Talking Points:
A charter is very valuable to help the implementation team think through and PLAN. (Refer everyone to the template charter.)
The charter helps to plan for the following things:
  The purpose of the program (e.g. What’s the overall aim of the strategy/program) and how it will be rolled out
  Key measures of the program (these can be a summary of evaluation metrics for the program)
  The scope of the program
  Key deliverables/milestones
  Implementation Team members and their roles and responsibilities.
  Stakeholders of the program
The charter ensures the entire team has the same assumptions and helps everyone clearly define the what so that everyone is on the same page
You can share the charter with your target audience as a “recruitment” tool as it provides them a high-level overview of the program
Share an experience: (refer to the iMAPP program charter)
Anytime we receive a grant or start a new program, one of the first things we do is create a charter. We have found that doing this uncovers all kinds of assumptions and helps the team quickly work through those assumptions.
A great example is the work we did with the Improvement Map project. The overall aim was to begin to create an online, interactive database for Evidence-based strategies. Upon receiving funding we put together a charter based on our assumptions. We help a meeting with the entire Improvement Map project team as well as the key funder and walked through each component of the charter. The program deliverables and project scope was a rich discussion and allowed us to share what we would be able to create and do for the specific amount of funding and time. It was a great opportunity to openly discuss expectations.
Participant interaction:
Ask if any of the participants have used a program charter.
If so ask them to share how they have used it, why it was helpful, and any lessons learned they would share.

## Slide 10: 2. Assess Organization/Coalition Readiness​
Do you have:
Supportive leaders?
Engaged partners?
Resources (money, staff, supplies)?
Staff with knowledge, skills, and enthusiasm?
Accounting and administrative structures?
System for monitoring progress/evaluation?
Refer to implementation guides and protocols for resources needed
Notes: Talking Points:
•In planning for implementation, you will need to get your organization prepared.
Ask the Audience:
•What are other ways you might assess your organization’s readiness for implementation?
•Share examples from experience about readiness or lack of readiness, if appropriate.
Examples to Share:
•Hiring staff or recruiting volunteers
•Engaging stakeholders in evaluation planning
•Program staff orientation
•Program/Policy/Strategy overview (e.g., core elements/components or key steps for implementation, outcomes)
•Materials
•Logistics
Talking Points:
•Strategize to engage leaders, purchase supplies, train staff, work with champion to engage staff, and plan for engaging partners.

## Slide 11: Assess Organizational Readiness
Readiness Checklist for Body and Soul
Notes: *Refer to Organizational Readiness Checklist as a reference (not as an activity). This tool can be shared as early as the Community Assessment or Selecting an Option modules.
Talking Points:
•This is an example of a tool that could be used to asses organizational readiness to implement an EBA. It can also help you improve your readiness by thinking about how to build your capacity to implement a program, policy, or strategy.
•The 1st column considers your capacity and resources such as staffing and training.
•You check the 2nd column for “Yes” if your organization already has this capacity.
•Check the 3rd column if you do not presently have this capacity, but could easily build capacity. For example you may easily be able to build capacity through a training, webinars, recruiting experts for the committee, or partnering more closely with a person or group in the immediate community, etc.
•The next column is “No” for “We do not have this capacity.” and it would be hard to obtain.
•The Comments field should capture reasons for the responses and brainstorm ideas how to build capacity.
•If your organization lacks capacity in many areas on the checklist, you could also reconsider if this EBA may not be the most compatible fit at this time.

## Slide 12: 3. Identify Early Adopters
Late Majority
35%
Early Majority
35%
Early Adopters
13%
Traditionalists
15%
2%
Innovators
Content Created by Population Health Improvement Partners
Everett Rogers’ Diffusion of Innovations
Notes: 12
Talking Points:
Everett Rogers a professor of communication studies, popularized the theory in his book Diffusion of Innovations. Based on his observations he developed the Diffusion of Innovation theory. He described 5 categories of adopters:
  Innovators: the first individuals to adopt an innovation. Innovators are willing to take risks, venter some, cope with uncertainty
  Early adopters-more integrated into social system…ones that others look to determine if they will try it—other look to them for advice
  Early majority-deliberate about things; not the leader (only tries something after they’ve seen that it works)
  Late majority-skeptical of things, more of a necessity than a choice, peer pressure is necessary
  Laggard-suspicious of new ideas; must be 100% certain it won’t fail; mandate it to happen
Practical Application and Participant Interaction
Facebook is great example of the diffusion of innovations theory and how things are adapted
Ask the audience to think about where they fell along the Diffusion Curve:
  Early Adopters—were willing to take the risk and see what Facebook was about
  Early Majority—you heard about Facebook but wanted to see what your friends thought about it before you used it
  Late Majority—you begin using it b/c everyone was talking about it and you felt like you were missing out on things
  Traditionalists---you still don’t have a Facebook account and don’t plan to have one in anytime soon.
Key Points
Think about these concepts as you begin to roll-out and test your strategy. Think about starting small and testing the strategy with the “early adopters” who would be willing to “take a risk” and try out something new.
It is important to note, that depending on what program/strategy, a person/organization may fall in different categories along the curve. For example, someone is an early adopter for Physical Activity strategies may be more of a traditionalist when it comes to Injury Prevention, etc.
Participant Interaction:
Who are the “early adopters” for your strategy?
What information do you need to share with the “early adopters” engage them in the strategy?

## Slide 13: APPLY IT!
Think about your strategy:
Who might be the “early adopters”?
What ways might you recruit the “early adopters”?
Share your thoughts with the group

## Slide 14: 4. Use Improvement Cycles to Learn What Works
Helps adapt good ideas to your specific situation:
  Forces us to think small
  Forces us to be methodical, make predictions and learn
  Allows rapid adaptation & implementation of changes
Notes: Talking Points
Using a structured approach (improvement cycles) to testing our ideas forces us to think small, think methodically, and document/learn as we go
Provides opportunity to understand what works and what needs improvement
Allows you to identify and correct issues in real time vs. waiting until the end of the strategy (If the specific strategy is experiencing barriers, you know immediately and can work with the target audience to address the barrier and identify how to move forward)
14

## Slide 15: Why Use Improvement Cycles?
Ideal
Reality
Ideal
Reality
Reality
Ideal
Content Created by Population Health Improvement Partners
Notes: Bridge from previous slide: Many people often ask..why should we test things using improvement cycles?
Engage Participants:
Ask participants to think about a program or personal endeavor that the planned.
Ask them to reflect on whether the activities turned out exactly as they had planned.
Allow a participant to share a quick story if time permits.
Give a real life example (Pinterest)
Give a real life example of how we have an ideal/vision/plan for something and it doesn’t turn out (e.g. Pinterest attempts)
For those of us who are addicted to Pinterest (and have no craftiness whatsoever) we see the ideal state/vision, but it doesn’t always turn at as planned. For example…I see this great idea for a kids craft and it’s supposed to look like this and ends up looking like that. Or a great photo idea….you want it to look like this and it ends up looking like this, with an upset baby and an overwhelmed/crying mom, or a cute little cake for the kids
Key Points to Emphasize:
Most often the exact plan/vision for a program isn’t exactly how things turn out.
We often have “Pinterest” type experiences in our public health programs/systems too. We have an ideal and vision for where we want to go, and we have great strategies to improve the system. However, many times there are unintended consequences that we can’t foresee and it can derail our efforts. It is important that we take the time to test our ideas on small scale and learn and adapt our ideas as we learn. Improvement Cycles help us avoid a “Pinterest” type fail in our programs. The results of failure can be devastating to our program--failure can often result in frustration and lack of buy-in
Improvement Cycles will help test things on a small scale and learn from issues and address them on a small scale

## Slide 16: Improvement (PDSA) Cycle
Act
Plan
Study
Do
Objective of cycle
Questions/predictions
Plan to carry out the cycle
(who, what, where, when)
Carry out the plan
Document problems/unexpected observations
Begin analysis of
data
Complete the analysis of data
Compare data to predictions
Summarize what was learned
What changes are to be made?
Adapt? Or Abandon?
Next cycle?
Use the PDSA cycle to test changes and organize feedback
Notes: 16
Bridge from the previous slide: The Plan Do Study Act cycle is a tool to help structure your improvement cycles. PDSA cycles help us to quickly learn and gather information that can be used to adapt or change the intervention components based on the data collection (Trial by Learning NOT Trial by Error)
Talking Points:
1) Provide background and define the PDSA cycle
The Plan Do Study Act cycle was made popular by Dr. Deming (father of quality improvement/management) Systematic way of gaining valuable learning and knowledge for the continual improvement of a product/program/ or process.
There are four steps in the PDSA (which was originally PDCA and Deming changed the C to Study to indicate that emphasis on using data to drive decision on how to improve a process/product.
The PDSA cycle is very similar to the scientific method (hypothesis, experiment, and evaluate), except it is used on a small scale in quick/rapid fashion to learn quickly
2) Discuss the core components and what happens during each component
Plan-during the plan portion-the implementation team determine what they want to learn by testing the specific strategy component. They define specific questions they want to address, make predications about what is going to happen with the test, and then make a plan for how the improvement cycle will be carried out (who, what, when, where) and how data will be collected (data collection can be very simple—asking for questions and feedback on how the process went). Planning is an important component of the PDSA cycle and most be done prior to testing something
Do-during this phase, the strategy component is test (as described in the Plan phase) and as it is being carried out—observations are document along with any barriers/challenges experience
Study-the team begins to review the data they have collected, compare it to the predictions they made, and summarize lessons learned
Act-based on the data collected, the team decides whether the strategy component should be: 1) adopted—it works great and there were no issues/challenges, 2) adapted-it worked well, but there are some things that should be tweaked to make it work better, or 3) abandoned-the strategy component didn’t work as intended and should be stopped immediately. Very rarely after testing something once do you automatically adopt or abandoned. More often-the team finds ways to adapt and test again.
Key Point to Emphasize:
In order to truly see the benefits of improvement cycles you must be diligent in following through with the entire PDSA cycle and document and acting on the lessons learned. You can’t just Plan and Do without Studying what you did and then ACTING upon the data you collected (quantitative or qualitative)
As you are rolling out new strategies, it is important to test things on a small scale and learn and adapt as you go. Try not to roll things out before testing them with improvement cycles.

## Slide 17: Rapid Cycles of Change
Hunches Theories Ideas
Changes That Result in Improvement
A
P
S
D
A
P
S
D
A
P
S
D
D
S
P
A
Learning
Very Small Scale Test
Follow-up Tests
Wide-Scale Tests of Change
Implementation of Change
Notes: 17
Bridge from previous slide: This picture provides a great visual of PDSAs in action.
Talking Points
Your implementation team starts out with a strategy or element that they test on a very small (1 person, 1 organization). Based on what the team learns from the 1st PDSA cycle they then adapt the component and test it again with the same person/organization or if they feel confident that the change will work, they expand and test with a larger group. The team continues to learn and test (expanding as they become more confident that the strategy component will work) until they are ready to role it out.
This concept is used in many industries (manufacturing, health care, IT)
  For example, in the IT world, researchers have found that the ultimate user experience is improved much more by 4 tests with 5 users than by a single test with 20 users. (Source: National Implementation Research Network)
Give a real world example:
Here is a very simple example of how you might use a PDSA in real life.
The strategy component/element-Create a brochure for the Stairways to Health that will be used in all state agency buildings
I would not want to create a brochure and post it in all state agencies. Instead I would start with one stairwell in one building (preferably a building that has staff that is supportive of the campaign and will give you good feedback)
Cycle # 1: Test the newly created brochure with someone in my own organization/program before a even put it into the stairwell
Cycle # 2 Based on the feedback/suggestion I would revise the brochure and test it with 5-10 additional staff within my own program.
Cycle # 3 Based on the feedback I would adapt the brochure and test it with 5-10 staff outside of my program
Cycle # 4 Based on the feedback I would adapt the brochure and test it with one entire building
Cycle # 5 Based on the feedback I would adapt and test it with a second building
Key Points:
Always start small
Capture learning/data and adapt based on the data collecting
As you get into more complex system changes (e.g. policies, etc. the setup for how you track your learning is a little more complicated and it may be take longer (e.g. weeks vs. days), but the PDSA cycle concept is the same)

## Slide 18: Plan and Do
Plan
  What do you want to change?
  Who should be involved?
Do
  What strategies will you test?
  Test the strategy
  Document results (baseline, process, outcomes)

## Slide 19: Study and Act
Study
  What did you learn?
  Did you meet your measurement goal?
Act
  What did you conclude from this cycle?
  Did it work?
    If yes, refine and scale up
    If no, select and try another strategy

## Slide 20: Activity: Practice a PDSA Cycle
In small groups, identify an adaptation you would want or need to make in strategy that you are testing.
  Refer to the PDSA Activity handout to answer questions
Notes: Instructions:
Let’s brainstorm about a small quality improvement project. Think about a strategy and consider the early parts of the cycle. You can use Body & Soul or FLU-FIT if you wish.
  Ask participants to select one of the intervention components and think through each step of the PDSA cycle using the PDSA cycle form. (10 mins)
  Ask several participants to report back on how they thought the PDSA cycle could be used to test the component
  As a facilitator—as the participants are reporting back, give feedback on their PDSA cycle (e.g. correct target audience, did they start small, how could they start smaller, etc.)

## Slide 21: 5. Draft an Implementation Plan
Review your SMART objectives
Review your organizational readiness assessment
Review information about the EBIs
Work with implementation team to draft a workplan for implementation
Notes: Talking Points:
•A work plan can be developed by considering the
•original program materials,
•readiness assessment,
•selection, and
•adaptation tools.
•Ideas about adaptation should be incorporated in the work plan.

## Slide 22: Components of an Implementation Plan
SMART Objectives
List of tasks or activities for each objective
Person responsible
Resources needed
Target completion dates
Indicator(s)/measures of completion or progress
Notes: Talking Points:
•In creating a work plan, you may want to create a table with the columns appropriate for your programs or policies. These are some examples:
•SMART Objective
•Activity
•Person responsible
•Resources Needed
•Due Date or Date Range
•Indicator(s) of completion or progress

## Slide 23: Example: Plan for Body and Soul
Notes: * Provide this as a handout so participants can see it. Presenter can modify using other examples.
Talking Points:
•Here is an example of a work plan for the Body & Soul program.
•A more legible hard copy should also be included in the materials.
*Walk through one row of this example if time permits:
•Let’s look at Row #2

## Slide 24: Maintenance
Plan for sustainability. Sustainability is the existence of structures and processes which allow a program to leverage resources to most effectively implement evidence-based policies and activities.
Luke D, Calhoun A, Herbers S. (Feb 2012). Building & Managing Sustainability in Public Health Programs. CDC Roundtable Presentation.
Everything a program needs to keep it going over time
Notes: Talking Points:
Maintenance plans should also be considered part of the work plan from the beginning program planning and in the midst of implementation.
Stakeholders should consider the realities and feasibility of what can be maintained long term with or without funding.
Example to Share:
Policies may not cost financial funds to continue, but may require staff time investment to remind, communicate, and enforce on an ongoing basis.

## Slide 25: Maintenance Activities
Leverage resources to sustain strategies over time:
Provide referrals for further service when needed
Seek additional funding
Maintain a program champion
Make the program a part of organizational services/policies
Conduct surveillance of the impact over time (e.g., track of smoking rates, BMI of children, screening)
Demonstrate return on investment/cost savings to justify investment of other stakeholders
Continue partnerships or build new ones to share costs and ongoing delivery of the intervention
Notes: Talking Points:
Leverage resources to sustain strategies over time.
Maintenance activities may include:
  Provide referrals for further service to other appropriate organizations or networks that already do similar work (e.g. referral to tobacco quitlines, community health centers).
  Seek additional funding (and collaborators that will strengthen funding proposals).
  Maintain or secure a program champion - preferably find multiple champions or those that can train protégés.
  Make program a part of organizational services/policies – integrate the EBS into existing annual infrastructure or annual plans.
  Surveillance of the impact over time (e.g., tracking of smoking rates, BMI of children, screening).
  Demonstrate return on investment/cost savings to justify investment of other stakeholders (e.g. patient reminders reduce no-show rates and lost revenue).
  Continue partnerships or build new ones to share costs and implementation delivery (e.g. one group may do outreach and partner with a clinic to do screenings).
Ask the Audience:
What are other ways you might seek to maintain activities long-term?

## Slide 26: Take-home Points:
Successful implementation requires advanced planning
Involve stakeholders from the beginning
Assess organizational readiness and build capacity
Use and adapt pre-existing guidance and tools
Improvement cycles (PDSAs) can be helpful to test changes and organize feedback
Use evaluation findings and lessons learned to plan for long-term sustainability
Notes: Talking Points:
Successful program implementation and evaluation requires detailed, advanced planning (i.e., workplans).
Partners and stakeholders should be involved from the beginning to implement with quality and higher levels of fidelity.
Planning for implementation should include assessing your organizational readiness and building capacity for readiness.
Implementation and evaluation of EBSs can utilize and adapt pre-existing plans, guidance and measurement tools from the original strategy.
Improvement cycles (like PDSA) can be helpful in testing changes and organizing feedback.
We should use our evaluation findings and lessons learned to plan for long-term sustainability.

## Slide 27: Questions?
Notes: Ask the Audience:
Do you have any questions?

## Slide 28: References
Durlak, J.A., & DuPre, E.P. (2008) Implementation matters: A review of research on the influence of implementation of program outcomes and the factors affecting implementation. Am J Com Psych. 41:327-350.
Luke D, Calhoun A, Herbers S. (Feb 2012). Building & Managing Sustainability in Public Health Programs. CDC Roundtable Presentation.
Schell, S.F., Luke, D.A., Schooley, M.W., Elliott, M.B., Herbers, S.H., Mueller, N.B., & Bunger, A.C. (2013). Public health program capacity for sustainability: A new framework. Implementation Science, 8(15).
Centers for Disease Control and Prevention. A Framework for Program Evaluation website. http://www.cdc.gov/eval/framework/.
Institute for Healthcare Improvement. http://www.ihi.org/